### Sitecore DevOps Pipeline MVP – 7 Week Project Plan

| Week | Phase | Task |
| --- | --- | --- |
| Week 1 | Project Kickoff & Readiness & Planning | Kickoff meeting with stakeholders |
|  |  | Define objectives and scope for Sitecore patching pipeline |
|  |  | Identify Sitecore environments and Azure subscriptions involved |
|  |  | Assess existing Sitecore deployments, Azure DevOps and backups strategy |
|  |  | Identify and document patching requirements for approvals and notifications |
| Week 2 | Pipeline Design & Source Prep | Design Azure DevOps project/repo pipeline architecture for patching process using automation scripts |
|  |  | Create Azure DevOps service connections to Azure Subscription |
|  |  | Define source location structure for deployable files |
|  |  | Create staging and backup folder structure and set up pipeline scaffolding (YAML/Classic) |
|  |  | Prepare script templates for backup and patching |
|  |  | Define secrets and variable groups for sensitive data if needed (SMTP, credentials) |
| Week 3 | Pipeline Implementation – Phase 1 | Implement backup process in Azure DevOps pipeline for the original Sitecore files before patching |
|  |  | Implement patch copy/update script step to patch files to target location |
|  |  | Validate the application (file checksum, timestamps, diff checks) mechanism after patching |
| Week 4 | Pipeline Implementation – Phase 2 | Implement IIS reset and App Pool restart script |
|  |  | Implement clickable Sitecore application URK for the smoke test browsing |
|  |  | Integrate email notification with dynamic URL in pipeline (SMTP/Graph API integration) |
|  |  | Finalize rollback and error-handling notifications |
| Week 5 | UAT & QA Testing & Sign off | Deploy pipeline to Dev/Test environments |
|  |  | Perform test patch deployments with mock updates |
|  |  | Conduct User Acceptance Testing with Admin Team |
|  |  | Incorporate feedback and perform fixes |
|  |  | Obtain sign-off from Sitecore product support team |
| Week 6 | Deployment Prep & Dry Run | Create/Prepare the Runbooks and Deployment Checklist for the final production/target patch package |
|  |  | Run full dry run on UAT/SIT environment (If Any is available) with full pipeline |
|  |  | Prepare User Guide and Admin Guide for future use include rollback strategy and testing validation report |
|  |  | Walkthrough with support/operations team |
| Week 7 | Production Rollout & Closure | Execute pipeline on Production/Target Sitecore environment |
|  |  | Monitor the application and validate patching success |
|  |  | test access post-patching and send email confirmation |
|  |  | Conduct lessons learned and improvement retrospective Close the project and submit final documentation. |